## Overview
Section | Item | Description
Project | Purpose | Build and test a multi-agent system for DermaMNIST classification, evaluation, enrichment, explanation, and review.
Project | Dataset | DermaMNIST v2: 10,015 RGB dermoscopic images, 28×28 pixels, seven classes.
Project | Task | Supervised seven-class image classification.
Project | Output | Predicted class, seven probabilities, uncertainty flag, attribution image, cited class information, and trace ID.
Scope | Included | Dataset audit, preprocessing, three classifiers, three agents, metrics, calibration, attribution, citations, final test, and review.
Scope | Excluded | Clinical diagnosis, treatment advice, hospital deployment, private patient data, and changes based on final test results.
Method | Development | Eight work packages. Each work package produces named deliverables and ends with a completion gate.
Method | Readiness | Integrated research software demonstrator. Research and education only.

## Objectives_RQs
Type | ID | Statement | Expected result
Objective | O1 | Verify the data basis. | Dataset registry, duplicate checks, class distribution, checksums, and preprocessing settings.
Objective | O2 | Build the classifier. | Three model configurations compared with the same training and evaluation settings.
Objective | O3 | Build the multi-agent workflow. | Agent1, Agent2, and Agent3 have defined inputs, outputs, tools, and responsibilities.
Objective | O4 | Verify prediction and explanation. | Metrics, uncertainty, attribution, citations, and traceable outputs.
Objective | O5 | Run and review the prototype. | Complete run, review checklist, and acceptance report.
Research question | RQ1 | Can the agents run reproducible experiments with fixed responsibilities and complete action records? | Agent records and reproducibility checks.
Research question | RQ2 | Which classifier gives the best class-balanced result? | Validation comparison across the three classifier families.
Research question | RQ3 | Can the system add cited class information and visual attribution without changing the classifier result? | Probability and trace checks in the final report.

## Work_Packages
WP | Name | Requires | Main work | Parallel work | Completion gate
WP01 | Research and Requirements | Project goal | Research, requirements, acceptance rules | - | Requirements approved
WP02 | Data | WP01 data requirements | Dataset registry, audit, preprocessing | WP05 source review | Data package accepted
WP03 | Training | WP02 data package | Model setup and Agent1 training | WP05 source preparation | Candidate models logged
WP04 | Evaluation | WP03 model set | Agent2 evaluation and model selection | WP05 integration | Selected model saved
WP05 | Enrichment and XAI | WP01 source policy + WP03 output schema | Agent3 class information and XAI | WP03 and WP04 | Class information and XAI verified
WP06 | Testing | WP04 selected model + WP05 module | Agent2 final test | - | Test report accepted
WP07 | Output | WP06 accepted outputs | Agent3 output and prototype run | - | Prototype demonstration passed
WP08 | Review | WP01-WP07 evidence | Agent3 review and acceptance | - | Critical findings closed

## Deliverables
Activity | Activity name | Responsible | Deliverable | Check
LA1.1 | State of the art | Reviewer | D1.1 | All cited papers are linked to a requirement or design choice.
LA1.2 | Requirements | Project Manager | D1.2 | Every mandatory requirement has an owner, verification method, and deliverable.
LA1.3 | Feasibility baseline | Technical Responsible | D1.3 | Data, models, agents, metrics, and test rules are fixed before implementation.
LA2.1 | Dataset registry | Technical Responsible | D2.1 | 10,015 images, seven labels, official partitions, dimensions, counts, and checksums verified.
LA2.2 | Integrity audit | Reviewer | D2.2 | Exact, near-duplicate, label, and cross-split findings logged with leakage policy.
LA2.3 | Data preparation | Technical Responsible | D2.3 | A clean run recreates split IDs, normalization, augmentation policy, and loaders.
LA3.1 | Model methods | Technical Responsible | D3.1 | Three classifier configurations use the same preprocessing, seeds, and metrics.
LA3.2 | Agent1 | Technical Responsible | D3.2 | Agent1 trains the three candidates and records each run.
LA3.3 | Automated training | Technical Responsible | D3.3 | Every run is reproducible; failures retain explicit reasons.
LA4.1 | Metric policy | Reviewer | D4.1 | Metrics, tie-breaks, calibration, and uncertainty rules fixed before selection.
LA4.2 | Agent2 evaluation | Technical Responsible | D4.2 | Agent2 compares the three candidates and selects one model.
LA4.3 | Model selection and freeze | Reviewer | D4.3 | Validation-only selection stores checksums, versions, and selection record.
LA5.1 | Source and explanation policy | Reviewer | D5.1 | Approved sources, citations, unsupported-claim behavior, and schema defined.
LA5.2 | Agent3 class information | Technical Responsible | D5.2 | Agent3 adds cited class information without changing the prediction.
LA5.3 | XAI integration | Technical Responsible | D5.3 | Attribution comes from the frozen model and shares the prediction trace ID.
LA6.1 | Agent2 testing | Technical Responsible | D6.1 | Agent2 tests the selected model with the specified metrics.
LA6.2 | Test protocol | Reviewer | D6.2 | Test set, metrics, failure rules, and output format are fixed before execution.
LA6.3 | System test | Reviewer | D6.3 | Metrics, calibration, robustness, and failure cases recorded without tuning.
LA7.1 | Agent3 output | Technical Responsible | D7.1 | Agent3 combines prediction, attribution, and cited class information.
LA7.2 | Output format | Project Manager | D7.2 | Prediction, probabilities, uncertainty, attribution, citations, and trace ID present.
LA7.3 | Prototype run | Project Manager | D7.3 | An unseen benchmark case runs end to end without manual intermediate edits.
LA8.1 | Agent3 review | Reviewer | D8.1 | Agent3 checks the required records and acceptance results.
LA8.2 | Final assessment | Reviewer | D8.2 | No critical finding remains open; limitations include consequences.

## Requirements
ID | Area | Requirement | Owner | Verification | Deliverable | Acceptance
REQ-DATA-01 | Data | Verify official file MD5, 10,015 records, 7 classes, 28×28 RGB, and official split sizes | Technical Responsible | Automated schema/count/checksum checks | D2.1 | A1
REQ-DATA-02 | Data | Log exact duplicates, perceptual-hash candidates, label conflicts, and cross-split overlap | Reviewer | Full-dataset audit with affected counts/rates | D2.2 | A1
REQ-DATA-03 | Data | Keep official benchmark split and define leakage-aware test exclusion without changing training | Reviewer | Policy plus parallel leakage-aware metrics | D2.2 | A1
REQ-DATA-04 | Data | Compute normalization on training images only and augment training only | Technical Responsible | Pipeline configuration and code test | D2.3 | A1
REQ-TRAIN-01 | Training | Compare three compact classifier families under one protocol | Technical Responsible | Three completed experiment records | D3.1,D3.3 | A3
REQ-TRAIN-02 | Training | Record seeds, parameters, history, checkpoints, checksums, failures, and code version | Technical Responsible | Experiment registry completeness | D3.3 | A2
REQ-AGENT-01 | Agents | Give Agent1, Agent2, and Agent3 explicit tasks, allowed tools, inputs, outputs, and limits | Technical Responsible | Specifications and unauthorized-tool unit test | D3.2,D4.2,D5.2,D6.1,D7.1,D8.1 | A2
REQ-TEST-01 | Testing | Prevent Agent1 from receiving final test labels | Reviewer | Interface inspection and event sequence | D3.2,D4.2,D6.3 | A5
REQ-EVAL-01 | Evaluation | Report accuracy, macro-F1, balanced accuracy, macro OvR AUROC, and per-class metrics | Reviewer | Metric schema checks | D4.1,D4.2,D6.3 | A4
REQ-EVAL-02 | Evaluation | Report confusion matrix, ECE, Brier score, and NLL | Reviewer | Metric ranges, dimensions, and plots | D4.1,D6.3 | A4
REQ-EVAL-03 | Evaluation | Select the highest validation macro-F1; use the listed tie-breakers when needed | Agent2 | Selection record recomputation | D4.2,D4.3 | A3
REQ-EVAL-04 | Evaluation | Set calibration and the uncertainty threshold from the validation split | Agent2 | Selected-model manifest fields | D4.2,D4.3 | A3,A5
REQ-XAI-01 | XAI | Generate attribution from the frozen classifier and link it to the prediction trace | Technical Responsible | Model checksum and trace equality | D5.3 | A6
REQ-SOURCE-01 | Enrichment | Use approved sources with title and URL for every class fact | Reviewer | Citation schema validation | D5.1,D5.2 | A6
REQ-SOURCE-02 | Enrichment | Never allow enrichment or explanation to modify class probabilities | Technical Responsible | Input/output equality assertion and unit test | D5.2,D7.1,D7.2 | A2,A6
REQ-OUTPUT-01 | Output | Return prediction, probabilities, uncertainty, attribution, citations, and trace ID | Project Manager | Case-report schema check | D7.2 | A6,A7
REQ-ROBUST-01 | Testing | Evaluate horizontal-flip and brightness perturbations | Agent2 | Robustness metric records | D6.2,D6.3 | A4
REQ-REVIEW-01 | Review | Block acceptance when any critical finding is open | Agent3 | Acceptance decision logic test | D8.1,D8.2 | A8
REQ-REPRO-01 | Reproducibility | Pin dependencies and record data, preprocessing, metric, model, and code versions | Technical Responsible | Clean verification plus version fields | D1.3,D3.3,D4.3,D6.3 | A3,A5
REQ-SCOPE-01 | Scope | Label all outputs research-only; omit diagnosis and treatment advice | Project Manager | README, policy, and case-report text checks | D5.1,D7.2 | A6

## Agents
Agent | Task | Inputs | Outputs | Allowed tools | Limit
Agent1 | Train the three classifier candidates | Training and validation data, model list, stop settings | Experiment records and model checkpoints | train_candidate, write_experiment_record | Cannot access final test labels
Agent2 | Evaluate candidates, select one model, and run the final test | Experiment records, validation data, selected model, and test data | Model selection, metrics, robustness results, and failure cases | evaluate_validation, freeze_model, verify_model_package, run_final_test | Cannot change the model after selection
Agent3 | Create class information, attribution, output, and review records | Prediction, attribution, class sources, and work-package records | Cited output, review checklist, and acceptance report | retrieve_approved_fact, compose_case_report, review_evidence | Cannot change the prediction or probabilities

## Technical
Area | Definition
Data | Official train, validation, and test splits; sample IDs, labels, image shape, class counts, and checksums recorded.
Data checks | Exact image hashes, 64-bit difference hashes, label conflicts, and cross-split matches.
Preprocessing | RGB values scaled to 0–1, training-channel normalization, and training augmentation.
Models | Compact ResNet-18, EfficientNet-B0, and ConvNeXt-Tiny for 28×28 input.
Training | Class-weighted cross-entropy, AdamW, fixed seed, early stopping, and saved run history.
Model selection | Highest validation macro-F1; balanced accuracy, macro-AUROC, and accuracy break ties.
Final test | Runs after model selection with fixed preprocessing, calibration, uncertainty threshold, and metrics.
Metrics | Accuracy, macro-F1, balanced accuracy, macro-AUROC, per-class precision/recall/F1, confusion matrix, ECE, Brier score, and NLL.
Robustness | Horizontal flip and ±10% brightness checks.
Attribution | Absolute input-gradient map from the selected classifier.
Enrichment | Class information from the approved source list. Each fact contains a title and URL.
Output | JSON prediction report and PNG attribution image.
Launcher 1 | Run the complete process. Missing DermaMNIST data are downloaded automatically.
Launcher 2 | Check and test the saved model with one input image.
Launcher 3 | Open the visual platform.
Visual platform | Choose Test trained model or Run full process, upload an image, and view each stage.

## Risks
ID | Risk | Impact | Trigger | Mitigation | Owner
R1 | Cross-split duplicates or leakage | High | Duplicate clusters cross partitions | Report official and leakage-aware results | Reviewer
R2 | Class imbalance hides weak classes | High | Aggregate and minority metrics diverge | Select with macro metrics and report each class | Technical + Reviewer
R3 | Overfitting during repeated experiments | High | Training improves while validation stalls | Fixed limits, early stopping, seeds, full history | Technical
R4 | Final test contamination | Critical | Test information appears before model selection | Restrict test access and rerun any affected result | Reviewer
R5 | Invalid agent tool or parameters | Medium | Schema rejection in log | Allow lists, typed parameters, explicit failure log | Technical
R6 | Wrong handoff record version | High | Trace or version mismatch | Schema and trace checks block mismatched handoff | Technical
R7 | Unsupported explanation | High | Statement has no approved source | Citation required; unsupported text omitted | Reviewer
R8 | XAI too coarse at 28×28 | Medium | Diffuse or unstable attribution | Label attribution coarse evidence only | Technical
R9 | Environment not reproducible | Medium | Clean run changes or dependencies fail | Pinned dependencies, checksums, seeds, regression tests | Technical

## Acceptance
ID | Item | Deliverables | Pass condition
A1 | Dataset identity and split audit | D2 | Official identity is verified and leakage findings have an explicit policy.
A2 | Agent roles and permissions | D3-D8 | All logged tools are authorized and handoffs use versioned records.
A3 | Model selection | D4 | The selection rule is set before testing and the selected model checksum is stored.
A4 | Class-balanced evaluation | D4, D6 | Accuracy, macro, per-class, calibration, and confusion metrics exist.
A5 | Final test | D6 | The final test runs after model selection with recorded settings and no retraining.
A6 | Explanation grounding | D5, D7 | Prediction, attribution, cited facts, and trace ID are linked.
A7 | Prototype run | D7 | An unseen benchmark sample runs end to end.
A8 | Final review | D8 | No critical finding remains open and limitations are recorded.

## References
ID | Authors | Title | Venue | Year | DOI or URL | Project use
1 | Yang et al. | MedMNIST v2 | Scientific Data | 2023 | https://doi.org/10.1038/s41597-022-01721-8 | Dataset and benchmark baseline
2 | Abhishek, Jain, Hamarneh | Investigating the Quality of DermaMNIST and Fitzpatrick17k | Scientific Data | 2025 | https://doi.org/10.1038/s41597-025-04382-5 | Duplicate/leakage controls
3 | Yan et al. | A multimodal vision foundation model for clinical dermatology | Nature Medicine | 2025 | https://doi.org/10.1038/s41591-025-03747-y | Scope distinction from large clinical models
4 | Chanda et al. | Dermatologist-like explainable AI enhances melanoma diagnosis accuracy | Nature Communications | 2025 | https://doi.org/10.1038/s41467-025-59532-5 | Explanation as evaluable output
5 | Dakhli and Barhoumi | Improving skin lesion classification through saliency-guided loss functions | Computers in Biology and Medicine | 2025 | https://doi.org/10.1016/j.compbiomed.2025.110299 | Classification and saliency
6 | Zuo, Wang, Wang | Adaptive multimodal fusion for skin lesion classification | Artificial Intelligence in Medicine | 2025 | https://doi.org/10.1016/j.artmed.2025.103091 | Uncertainty and per-class evaluation
7 | Nahm et al. | Artificial Intelligence in Dermatology | International Journal of Dermatology | 2025 | https://doi.org/10.1111/ijd.17847 | Clinical implementation limitations
8 | Han et al. | Planet-wide performance of a skin disease AI algorithm | npj Digital Medicine | 2025 | https://doi.org/10.1038/s41746-025-01980-w | Distribution and real-world performance
9 | Li et al. | Dataset nutrition label for dermatologic AI | npj Digital Medicine | 2025 | https://doi.org/10.1038/s41746-025-02125-9 | Dataset documentation
10 | Ferber et al. | Autonomous AI agent for oncology | Nature Cancer | 2025 | https://doi.org/10.1038/s43018-025-00991-6 | Tool orchestration
11 | Chen et al. | Multi-agent conversational diagnostic capability | npj Digital Medicine | 2025 | https://doi.org/10.1038/s41746-025-01550-0 | Multi-agent reasoning
12 | Laiouar-Pedari et al. | Prospective evidence on AI-assisted melanoma diagnostics | JAMA Dermatology | 2026 | https://doi.org/10.1001/jamadermatol.2026.0217 | Prospective evidence limits
13 | Anriot et al. | Limits of AI models for skin cancer diagnosis | JAMA Dermatology | 2026 | https://doi.org/10.1001/jamadermatol.2026.1492 | Realistic-setting limitations
14 | Collaco et al. | Agentic AI in healthcare: scoping review | npj Digital Medicine | 2026 | https://doi.org/10.1038/s41746-026-02517-5 | Agent safety and validation gaps
15 | Yu et al. | Multimodal AI agents in healthcare | npj Digital Medicine | 2026 | https://doi.org/10.1038/s41746-026-03060-z | Agent evidence maturity
16 | Schmidgall et al. | AgentClinic | npj Digital Medicine | 2026 | https://doi.org/10.1038/s41746-026-02674-7 | Sequential tool-use risk